## Sprint Backlog
Sprint Goal
Start the first step in building the app by creating accounts and view the restaurants list to the user. Moreover, the ability to search in this list.
# | Sprint backlog | Tasks | Estimated velocity | DoD | Estimate the capacity | Status
1 | As a user , I want to create account so that I can access the application features | 1.1- Validate the existence of the email. 1.2- Validate the password format then hash it. 1.3- Add the user account and his hashed password to the database. | 6 Days | when creating account I found it in the data base with the hashed pasword | 2 | ready
2 | As a user , I want to view restaurants so that I can see the different restaurants available | 2.1- Create a list of restaurants 2.2- Make the list accessable by users | 5 Days | View the restaurants list with created account | 2 | ready
3 | As a user , I want to search restaurants so that I can find specific restaurant | 3.1- build function that searches in restaurants list | 3 Days | Search for restaurant in the list (case unsensitive) and find it. | 2 | to-do | to-do as it is depend on the previous user story